**QEP and SACSCOC Reaffirmation**

**Presented at the Faculty Senate Meeting on 10/15/21, Virtual**

**In 2022** there will be two separate opportunities for broad engagement of the faculty:

(a) Working on QEP

(b) Working on Standards

**QEP** - **Timeline**

|  |  |
| --- | --- |
| **Date** | **Action/Outcome** |
| October 31, 2021 | Send out survey/Request for Proposals to solicit faculty ideas about QEP; the RFP questions/sections will be based on SACSCOC QEP-related documents  *Submitting a proposal will count towards faculty service* |
| December 1, 2021 | Form a working group (#1) that will review the QEP proposals; the working group develops/agrees on detailed rubric(s) for rating of the proposals |
| January 17, 2022 | Deadline to submit QEP proposals |
| January – February 2022 | The working group (#1) reviews QEP proposals for feasibility  *Participation on workgroup #1 will count towards faculty service* |
| February 15, 2022 | Deadline to identify feasible QEP proposals, ranked |
| February – March, 2022 | Review of top 3 feasible proposals by the Faculty Senate Executive Committee & Executive Administrative Council |
| April 15, 2022 | Target date for announcing the selected QEP proposal |
| May – July, 2022 | Form a workgroup (#2) to work on QEP implementation. Develop timeline for QEP implementation. |
| August – Dec, 2022 | Workgroup (#2) - Develop detailed QEP implementation plan with outcomes  *Participation on workgroup #2 will count towards faculty service; most of that work will be completed in Fall 2022; the Leader of this workgroup is expected to carry the heaviest work and will receive either workload adjustment or a stipend* |
| Spring semester 2023 | QEP pilot |
| November 30, 2023 | QEP ready for submission |

**Reaffirmation** - **Timeline**

|  |  |
| --- | --- |
| **Track B—Undergraduate and Graduate Degrees or Graduate Degrees Only** | |
| ***2021*** | |
| During the SACSCOC Annual Meeting (December 5-7. 2021) | Orientation of Leadership Teams Institutional Summary Form due |
| *2023* | |
| September 8, 2023 | Compliance Certification and updated Institutional Summary Form due |
| October 1, 2023 | External QEP reviewers – 2 names submitted to SACSCOC |
| First full week in November,  November 7-9, 2023 | Off-site review conducted |
| Six weeks prior to on-site review  Earliest visit is January 22 – QEP must be ready before December 11, 2023 –  Best to be ready by end of November 2023 | Quality Enhancement Plan, Focused Report, and updated Institutional Summary Form due |
| *2024* | |
| Mid-January through the third week of April  January 22 – April 12, 2024 | On-site review period |
| Five months after visit | Response due, if applicable |
| First week in December  December 2-5, 2024 | Review by SACSCOC Board of Trustees |